## Sheet1
Sprint Burndown Chart - Week 6
Task ID | Task Description | Initial Estimate | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design and add a volcano to the map (Madalena, Renata) | Day 0: 5; Day 4: 1.6; Day 5: 0.4; Day 7: 1.6
2 | Analyse the code to find the areas of interest (Madalena, Renata) | Day 0: 1; Day 4: 0.4; Day 6: 0.4; Day 7: 0.4
3 | Design and add the WagonTrain with a horse (Beatriz, Catarina P.) | Day 0: 1; Day 7: 0.6
4 | Analyse the code to find the areas of interest (Beatriz, Catarina P.) | Day 0: 2; Day 2: 1; Day 5: 0.6; Day 7: 0.4
5 | Design and add a plague in a colony (Catarina C., Joana) | Day 0: 4; Day 6: 0.3; Day 7: 0.2
6 | Analyse the code to find the areas of interest (Catarina C., Joana) | Day 0: 1.5; Day 6: 0.2; Day 7: 0.2
Completed Effort |  | 0 | 0 | 1 | 0 | 2 | 1 | 0.9 | 3.4
Remaining Effort |  | 14.5 | 14.5 | 13.5 | 13.5 | 11.5 | 10.5 | 9.6 | 6.2
Ideal Burndown |  | 14.5 | 12.4286 | 10.3571 | 8.2857 | 6.2143 | 4.1429 | 2.0714 | 0