## Sheet1
Sprint Burndown Chart - Week 7
Task ID | Task Description | Initial Estimate | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Understand how the tiles are programmed and how the methods work with each other (Madalena, Renata) | bar: Day 0; Day 2
2 | Getting the explored volcanos by non-AI players (Madalena, Renata) | Day 0: 2.5; Day 2: 0.5; Day 3: 1; Day 4: 1.5
3 | Implementing the lifespan of volcanos based on turns (Madalena, Renata) | Day 0: 1; Day 4: 0.5; Day 5: 0.5
4 | Implementing the volcanos' tranformation into mountains (Madalena, Renata) | Day 0: 0.5; Day 5: 0.7
5 | Implementing the limit of turns for the Wagon Train (Beatriz, Catarina P.) | Day 0: 1; Day 3: 1; Day 4: 0.5
6 | Implementing the increase of moves per turn with the Wagon Train with horses (Beatriz, Catarina P.) | bar: Day 0 to Day 1
7 | Implementing the decrease of "holds" in a Wagon Train overtime (Beatriz, Catarina P.) | Day 0: 3; Day 4: 0.5; Day 5: 0.5
8 | Choose where the tiles where the plague happens (Catarina C., Joana) | Day 0: 1.5; Day 4: 0.2; Day 5: 2
9 | Implement plague effect (Catarina C., Joana) | Day 0: 2.5; Day 4: 0.4
10 | Unit Tests (Madalena, Renata) | Day 0: 2; Day 6: 1
11 | Unit Tests (Beatriz, Catarina P.) | Day 0: 2; Day 5: 1; Day 6: 0.5
12 | Unit Tests (Catarina C., Joana) | Day 0: 2
13 | Use case for proposed extension (Madalena, Renata) | Day 0: 1; Day 5: 0.6
14 | Use case for proposed extension (Beatriz, Catarina P.) | Day 0: 1; Day 3: 0.6
15 | Use case for proposed extension (Catarina C., Joana) | Day 0: 1; Day 7: 0.2
16 | Final doc for delivery | Day 0: 3; Day 6: 1; Day 7: 2
17 | Demo Video (Beatriz, Catarina P.) | Day 0: 0.2; Day 6: 0.2
18 | Demo Video (Madalena, Renata) | Day 0: 0.7; Day 6: 0.7
19 | Demo Video (Catarina C., Joana) | Day 0: 0.2; Day 7: 0.1
20 | Edit demo video and record voiceover (Catarina P.) | Day 0: 0.3; Day 6: 0.2
Completed Effort |  | 0 | 1 | 1.5 | 2.6 | 3.6 | 5.3 | 3.6 | 2.1
Remaining Effort |  | 27.4 | 26.4 | 24.9 | 22.3 | 18.7 | 13.4 | 9.8 | 7.7
Ideal Burndown |  | 27.4 | 23.4857 | 19.5714 | 15.6571 | 11.7429 | 7.8286 | 3.9143 | 0