## Sheet1
Sprint Burndown Chart - Week 5
Task ID | Task Description | Initial Estimate | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Read the reviews on the reports (Beatriz) | Day 0: 0.1; Day 3: 0.1
2 | Update reports (Beatriz) | Day 0: 0.5; Day 4: 0.2; Day 6: 0.1; Day 7: 0.3
3 | Read the reviews on the reports (Catarina C.) | Day 0: 0.1; Day 4: 0.1
4 | Update reports (Catarina C.) | Day 0: 0.3
5 | Read the FreeCol's documentation and write report on use cases (Catarina C.) | Day 0: 1; Day 1: 0.2; Day 5: 0.3
6 | Search for and write report on design patterns in the code (Catarina C.) | Day 0: 0.5; Day 6: 0.4; Day 7: 0.3
7 | Read the reviews on the reports (Catarina P.) | Day 0: 0.1; Day 1: 0.1
8 | Update reports (Catarina P.) | Day 0: 0.3; Day 2: 0.3
9 | Read the reviews on the reports (Joana) | Day 0: 0.1; Day 1: 0.1
10 | Update reports (Joana) | Day 0: 0.3; Day 2: 0.3
11 | Read the FreeCol's documentation and write report on use cases (Joana) | Day 0: 0.5; Day 3: 0.2; Day 4: 0.4
12 | Read the reviews on the reports (Madalena) | Day 0: 0.1; Day 2: 0.1
13 | Update reports (Madalena) | Day 0: 0.5; Day 4: 0.1; Day 7: 0.3
14 | Read the reviews on the reports (Renata) | Day 0: 0.1; Day 3: 0.1
15 | Update reports (Renata) | Day 0: 0.4; Day 7: 0.4
16 | Distribute the User Stories between groups of 2 | Day 0: 0.2; Day 6: 0.2
Completed Effort |  | 0 | 0.4 | 0.7 | 0.4 | 0.8 | 0.3 | 0.7 | 1.3
Remaining Effort |  | 5.1 | 4.7 | 4 | 3.6 | 2.8 | 2.5 | 1.8 | 0.5
Ideal Burndown |  | 5.1 | 4.3714 | 3.6429 | 2.9143 | 2.1857 | 1.4571 | 0.72857 | 0