## Sheet1
Sprint Burndown Chart - Week 2
Task ID | Task Description | Initial Estimate | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Setup game | Day 0: 1.5; Day 1: 1.5
2 | Play the game | 6 |  | 1 | 1 | 1 | 1 | 1 | 1
3 | Read the class powerpoints for a better undersanting of how to write User Stories | Day 0: 2; Day 1: 2
4 | Prepare ideas for the extra functionalities (Beatriz) | Day 0: 0.75; Day 2: 0.25; Day 5: 0.5
5 | Prepare ideas for the extra functionalities (Catarina C.) | Day 0: 0.3; Day 2: 0.3
6 | Prepare ideas for the extra functionalities (Catarina P.) | Day 0: 0.5; Day 4: 0.5
7 | Prepare ideas for the extra functionalities (Joana) | Day 0: 0.3; Day 1: 0.1; Day 3: 0.2
8 | Prepare ideas for the extra functionalities (Madalena) | Day 0: 1.5; Day 3: 0.25; Day 4: 0.5; Day 5: 0.75
9 | Prepare ideas for the extra functionalities (Renata) | Day 0: 1; Day 3: 0.25; Day 4: 0.5; Day 5: 0.25
10 | Discuss about functionalities prepared | Day 0: 0.5; Day 5: 0.25; Day 6: 0.5
11 | Choose and write 3 User Stories | Day 0: 0.3; Day 6: 0.3
12 | Get feedback from the teacher about the chosen User Stories | Day 0: 0.1; Day 6: 0.1
13 | Update the User Stories | Day 0: 0.2; Day 6: 0.3
14 | Create repository in GitHub (Renata) | Day 0: 0.25; Day 1: 0.25
15 | Add Project_Management folders in the repository (Madalena) | Day 0: 0.1; Day 5: 0.1
16 | Submit the file with the 3 User Stories (Catarina P.) | Day 0: 0.1; Day 6: 0.1
Completed Effort |  | 0 | 3.85 | 1.55 | 1.7 | 2.5 | 2.85 | 2.3 | 1
Remaining Effort |  | 15.4 | 11.55 | 10 | 8.3 | 5.8 | 2.95 | 0.65 | -0.35
Ideal Burndown |  | 15.4 | 13.2 | 11 | 8.8 | 6.6 | 4.4 | 2.2 | 0