## Sheet1
Sprint Burndown Chart - Week 3
Task ID | Task Description | Initial Estimate | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Read the class powerpoints for a better undersanting of code smells | Day 0: 1; Day 1: 0.8; Day 2: 0.4
2 | Read the class powerpoints for a better undersanting of design patterns | Day 0: 2; Day 1: 1; Day 2: 1.3
3 | Read the class powerpoints for a better undersanting of use case diagrams | Day 0: 2; Day 1: 0.7; Day 2: 0.5
4 | Distribute the code metrics | Day 0: 0.1; Day 3: 0.1
5 | Get feedback from the teacher about the chosen User Stories | Day 0: 0.1; Day 6: 0.1
6 | Update the User Stories | Day 0: 0.4; Day 6: 0.1; Day 7: 0.3
7 | Search for design patterns in the code | Day 0: 6; Day 5: 2; Day 7: 4
8 | Search for code smells in the code | Day 0: 6; Day 5: 1; Day 7: 4
9 | Read the FreeCol's documentation to help create use cases | Day 0: 4; Day 7: 3.5
Completed Effort |  | 0 | 2.5 | 2.2 | 0.1 | 0 | 3 | 0.2 | 11.8
Remaining Effort |  | 21.6 | 19.1 | 16.9 | 16.8 | 16.8 | 13.8 | 13.6 | 1.8
Ideal Burndown |  | 21.6 | 18.5143 | 15.4286 | 12.3429 | 9.2571 | 6.1714 | 3.0857 | 0