## Sheet1
Sprint Burndown Chart - Week 4
Task ID | Task Description | Initial Estimate | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Search for and write report on design patterns in the code (Beatriz) | 2 | 0.6 | 0.7 | 0.5 | 0.1 | 0.2
2 | Search for and write report on code smells in the code (Beatriz) | 1.5 | 0.2 | 0.1 | 0.1 | 0.5
3 | Read the FreeCol's documentation and write report on use cases (Beatriz) | Day 0: 0.8; Day 4: 0.4; Day 5: 0.1
4 | Write report on the code metrics (Beatriz) | 0.5 | 0.1 | 0.2 |  |  | 0.1 |  | 0.2
5 | Write report reviews (Beatriz) | Day 0: 0.2; Day 5: 0.1
6 | Search for and write report on design patterns in the code (Catarina C.) | 2 | 0.3 | 0.3 | 0.5 |  | 0.4
7 | Search for and write report on code smells in the code (Catarina C.) | 1.5 | 0.3 | 0.5 | 0.5 |  | 0.4
8 | Read the FreeCol's documentation and write report on use cases (Catarina C.) | bar: Day 0
9 | Write report on the code metrics (Catarina C.) | Day 0: 0.5; Day 2: 0.2; Day 4: 0.2; Day 5: 0.1
10 | Write report reviews (Catarina C.) | Day 0: 0.2; Day 5: 0.1
11 | Search for and write report on design patterns in the code (Catarina P.) | 2 | 0.4 | 0.7 |  | 0.7 | 0.3
12 | Search for and write report on code smells in the code (Catarina P.) | Day 0: 1; Day 1: 0.4; Day 2: 0.1
13 | Read the FreeCol's documentation and write report on use cases (Catarina P.) | Day 0: 0.5; Day 4: 0.2; Day 5: 0.3
14 | Write report on the code metrics (Catarina P.) | Day 0: 0.7; Day 1: 0.2; Day 2: 0.2; Day 5: 0.1
15 | Write report reviews (Catarina P.) | Day 0: 0.2; Day 5: 0.2
16 | Search for and write report on design patterns in the code (Joana) | 2 | 0.4 | 0.5 |  | 0.2 | 0.3
17 | Search for and write report on code smells in the code (Joana) | Day 0: 1; Day 1: 0.2; Day 3: 0.1
18 | Read the FreeCol's documentation and write report on use cases (Joana) | Day 0: 0.7
19 | Write report on the code metrics (Joana) | Day 0: 0.5; Day 1: 0.2; Day 2: 0.3; Day 5: 0.1
20 | Write report reviews (Joana) | Day 0: 0.2; Day 5: 0.2
21 | Search for and write report on design patterns in the code (Madalena) | 1.5 | 0.6 | 0.2 | 0.6 | 0.2
22 | Search for and write report on code smells in the code (Madalena) | Day 0: 1; Day 1: 0.4; Day 3: 0.4
23 | Read the FreeCol's documentation and write report on use cases (Madalena) | Day 0: 1; Day 4: 0.7; Day 5: 0.4
24 | Write report on the code metrics (Madalena) | Day 0: 1; Day 2: 0.8; Day 4: 0.1
25 | Write report reviews (Madalena) | Day 0: 0.2; Day 5: 0.3
26 | Search for and write report on design patterns in the code (Renata) | 2 | 0.4 | 0.5 |  | 0.4 | 0.2
27 | Search for and write report on code smells in the code (Renata) | 1 | 0.2 | 0.1 | 0.4 | 0.3
28 | Read the FreeCol's documentation and write report on use cases (Renata) | Day 0: 1; Day 5: 0.4
29 | Write report on the code metrics (Renata) | Day 0: 0.5; Day 4: 0.3; Day 5: 0.2
30 | Write report reviews (Renata) | Day 0: 0.2; Day 5: 0.2
Completed Effort |  | 0 | 4.9 | 5.4 | 3.1 | 4.3 | 4.7 | 0 | 0.2
Remaining Effort |  | 28.4 | 23.5 | 18.1 | 15 | 10.7 | 6 | 6 | 5.8
Ideal Burndown |  | 28.4 | 24.3429 | 20.2857 | 16.2286 | 12.1714 | 8.1143 | 4.0571 | 0